## Stories
DT | DT_SPRINT | SPRINT | Issue_Type | Summary | Key | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due_date | parent | Resolved | Status_Category_Changed | Linked_Issues | Parent_Link | Time Resolution
2021-02-26 |  |  | Build Story | Develop Report for the Optimization of Oracle Database License Cost | DBAAS-4923 | Eduardo Silva | Erik Solis | High | Blocked |  | 2021-02-26 | 2021-11-03 | 2021-11-05 | DBAAS-4507 |  | 2021-09-23 |  |  | 0
2021-06-21 | 2021-06-21 | DBAAS-5814 | [16 empty] | 0
2021-06-22 |  |  | Feature | DBaaS Database Instance Account Attestation Web Application | DBAAS-5814 | Julio Alcala | Pooja Chanana | Medium | in Build |  | 2021-06-22 | 2021-10-20 | 2021-12-17 |  |  | 2021-07-12 | DBAAS-5810 |  | 0
2021-06-22 |  |  | Enabler Story | Conceptualize Design for DBAAS5814 | DBAAS-5815 | Alex Gomez | Automation for Jira | Medium | Done | Done | 2021-06-22 | 2021-09-20 |  | DBAAS-5814 | 2021-09-20 | 2021-09-20 |  |  | 90
2021-06-24 |  |  | Enhancement | Enhance the DBaaS Database Assets Report with Additional Columns | DBAAS-5835 | Eduardo Silva | Pooja Chanana | Medium | Done | Done | 2021-06-24 | 2021-07-17 | 2021-09-17 |  | 2021-07-16 | 2021-07-16 | DBAAS-6164 |  | 22
2021-07-06 |  |  | Subtask | Install Slack Client | DBAAS-6024 | Fabian Ponce | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-12 |  | DBAAS-6004 | 2021-07-12 | 2021-07-12 |  |  | 6
2021-07-06 |  |  | Subtask | Update GAL and Profile Information | DBAAS-6023 | Fabian Ponce | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-12 |  | DBAAS-6004 | 2021-07-12 | 2021-07-12 |  |  | 6
2021-07-06 |  |  | Subtask | Install the Zscaler tool | DBAAS-6010 | Fabian Ponce | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-12 |  | DBAAS-6004 | 2021-07-12 | 2021-07-12 |  |  | 6
2021-07-06 |  |  | Subtask | Install tools on developer workstation | DBAAS-6009 | Fabian Ponce | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-15 |  | DBAAS-6004 | 2021-07-15 | 2021-07-15 |  |  | 9
2021-07-06 |  |  | Subtask | Request cloud platform server admin account | DBAAS-6008 | Fabian Ponce | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-15 |  | DBAAS-6004 | 2021-07-15 | 2021-07-15 |  |  | 9
2021-07-06 |  |  | Subtask | Review and understand important DBaaS documentation (policies procedures user guides etc.) | DBAAS-6007 | Fabian Ponce | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-15 |  | DBAAS-6004 | 2021-07-15 | 2021-07-15 |  |  | 9
2021-07-06 |  |  | Subtask | Install Slack Client | DBAAS-6068 | Alex Gomez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-12 |  | DBAAS-6048 | 2021-07-12 | 2021-07-12 |  |  | 6
2021-07-06 |  |  | Subtask | Update GAL and Profile Information | DBAAS-6067 | Alex Gomez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-12 |  | DBAAS-6048 | 2021-07-12 | 2021-07-12 |  |  | 6
2021-07-06 |  |  | Subtask | Install the Zscaler tool | DBAAS-6054 | Alex Gomez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-15 |  | DBAAS-6048 | 2021-07-15 | 2021-07-15 |  |  | 9
2021-07-06 |  |  | Subtask | Install tools on developer workstation | DBAAS-6053 | Alex Gomez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-08-05 |  | DBAAS-6048 | 2021-08-05 | 2021-08-05 |  |  | 30
2021-07-06 |  |  | Subtask | Request cloud platform server admin account | DBAAS-6052 | Alex Gomez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-08-05 |  | DBAAS-6048 | 2021-08-05 | 2021-08-05 |  |  | 30
2021-07-06 |  |  | Subtask | Review and understand important DBaaS documentation (policies procedures user guides etc.) | DBAAS-6051 | Alex Gomez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-21 |  | DBAAS-6048 | 2021-07-21 | 2021-07-21 |  |  | 15
2021-07-06 |  |  | Subtask | Install Slack Client | DBAAS-6046 | Eduardo Silva | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-6026 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Update GAL and Profile Information | DBAAS-6045 | Eduardo Silva | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-6026 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Install the Zscaler tool | DBAAS-6032 | Eduardo Silva | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-6026 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Install tools on developer workstation | DBAAS-6031 | Eduardo Silva | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-6026 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Request cloud platform server admin account | DBAAS-6030 | Eduardo Silva | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-6026 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Review and understand important DBaaS documentation (policies procedures user guides etc.) | DBAAS-6029 | Eduardo Silva | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-6026 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Install Slack Client | DBAAS-5980 | Ricardo Martinez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-5960 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Update GAL and Profile Information | DBAAS-5979 | Ricardo Martinez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-5960 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Install the Zscaler tool | DBAAS-5966 | Ricardo Martinez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-5960 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Install tools on developer workstation | DBAAS-5965 | Ricardo Martinez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-14 |  | DBAAS-5960 | 2021-07-14 | 2021-07-14 |  |  | 8
2021-07-06 |  |  | Subtask | Request cloud platform server admin account | DBAAS-5964 | Ricardo Martinez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-16 |  | DBAAS-5960 | 2021-07-16 | 2021-07-16 |  |  | 10
2021-07-06 |  |  | Subtask | Review and understand important DBaaS documentation (policies procedures user guides etc.) | DBAAS-5963 | Ricardo Martinez | Derek Daigrepont | Medium | Done | Done | 2021-07-06 | 2021-07-16 |  | DBAAS-5960 | 2021-07-16 | 2021-07-16 |  |  | 10
2021-07-16 |  |  | Enhancement | Enhance the DBaaS Database Assets Report with Auto Minor Version Update Column | DBAAS-6164 | Eduardo Silva | Pooja Chanana | Medium | Blocked |  | 2021-07-16 | 2021-10-22 | 2021-09-17 |  |  | 2021-07-16 | DBAAS-2263;DBAAS-5835 |  | 0
2021-07-20 |  |  | Build Story | Develop the Power BI Database Instance Recoverability report | DBAAS-6224 | Miguel Martinez | Pooja Chanana | Medium | Ready for Analysis |  | 2021-07-20 | 2021-10-22 | 2021-11-05 | DBAAS-6943 |  | 2021-07-20 |  |  | 0
2021-07-20 |  |  | Enabler Story | Design the Power BI Database Instance Recoverability report | DBAAS-6223 | Miguel Martinez | Pooja Chanana | Medium | Ready for Analysis |  | 2021-07-20 | 2021-10-22 |  | DBAAS-6943 |  | 2021-07-20 |  |  | 0
2021-07-20 |  |  | Build Story | Develop the Stored Procedure to produce the Dataset for the Power BI report | DBAAS-6222 | Miguel Martinez | Pooja Chanana | Medium | Ready for Analysis |  | 2021-07-20 | 2021-10-22 |  | DBAAS-6943 |  | 2021-07-20 |  |  | 0
2021-07-27 | 2021-07-27 | Research Capabilities | Enabler Story | Prototype attestation web app hosted in Microsoft PowerApps | DBAAS-6292 | Fabian Ponce | Derek Daigrepont | Medium | Done | Done | 2021-07-27 | 2021-08-27 |  | DBAAS-5814 | 2021-08-27 | 2021-08-27 | DBAAS-6289 |  | 31
2021-07-27 | 2021-07-27 | Research Capabilities | Enabler Story | Research capabilities of hosting attestation web app via Microsoft PowerApps | DBAAS-6289 | Fabian Ponce | Derek Daigrepont | Medium | Done | Done | 2021-07-27 | 2021-08-09 |  | DBAAS-5814 | 2021-08-09 | 2021-08-09 | DBAAS-6292 |  | 13
2021-07-28 |  |  | Enabler Story | Research the capability to create a ticket in ServiceNow from the chosen web tool | DBAAS-6306 | Fabian Ponce | Pooja Chanana | Medium | Blocked |  | 2021-07-28 | 2021-10-22 |  | DBAAS-5814 |  | 2021-10-22 | DBAAS-6518 |  | 0
2021-08-03 |  |  | Enhancement | Update Managed DBaaS Support Cost Forecast Report | DBAAS-6319 | Eduardo Silva | Pooja Chanana | Medium | Done | Done | 2021-08-03 | 2021-09-27 |  |  | 2021-08-03 | 2021-08-03 |  |  | 0
2021-08-05 |  |  | Subtask | Install Slack Client | DBAAS-6369 | Julio Alcala | Derek Daigrepont | Medium | Done | Done | 2021-08-05 | 2021-09-02 |  | DBAAS-6349 | 2021-09-02 | 2021-09-02 |  |  | 28
2021-08-05 |  |  | Subtask | Update GAL and Profile Information | DBAAS-6368 | Julio Alcala | Derek Daigrepont | Medium | Done | Done | 2021-08-05 | 2021-09-02 |  | DBAAS-6349 | 2021-09-02 | 2021-09-02 |  |  | 28
2021-08-05 |  |  | Subtask | Install the Zscaler tool | DBAAS-6355 | Julio Alcala | Derek Daigrepont | Medium | Done | Done | 2021-08-05 | 2021-08-12 |  | DBAAS-6349 | 2021-08-12 | 2021-08-12 |  |  | 7
2021-08-05 |  |  | Subtask | Install tools on developer workstation | DBAAS-6354 | Julio Alcala | Derek Daigrepont | Medium | Done | Done | 2021-08-05 | 2021-09-02 |  | DBAAS-6349 | 2021-09-02 | 2021-09-02 |  |  | 28
2021-08-05 |  |  | Subtask | Request cloud platform server admin account | DBAAS-6353 | Julio Alcala | Derek Daigrepont | Medium | Done | Done | 2021-08-05 | 2021-09-02 |  | DBAAS-6349 | 2021-09-02 | 2021-09-02 |  |  | 28
2021-08-05 |  |  | Subtask | Review and understand important DBaaS documentation (policies procedures user guides etc.) | DBAAS-6352 | Julio Alcala | Derek Daigrepont | Medium | Done | Done | 2021-08-05 | 2021-08-18 |  | DBAAS-6349 | 2021-08-18 | 2021-08-18 |  |  | 13
2021-08-06 | 2021-08-06 | 1rst. Iteration | [16 empty] | 0
2021-08-09 |  |  | Enhancement | Update Power BI Report: Managed DBaaS Product Rate Card | DBAAS-6387 | Eduardo Silva | Pooja Chanana | Medium | Done | Done | 2021-08-09 | 2021-09-27 |  |  | 2021-08-11 | 2021-08-11 | DBAAS-6385 |  | 2
2021-08-11 |  |  | Enhancement | Update Managed DBaaS Support Cost Forecast Power BI report | DBAAS-6402 | Ricardo Martinez | Pooja Chanana | Medium | Done | Done | 2021-08-11 | 2021-09-27 |  |  | 2021-08-13 | 2021-08-13 |  |  | 2
2021-08-12 |  |  | Enhancement | Update Managed DBaaS Product Rate Card Power BI report | DBAAS-6411 | Eduardo Silva | Pooja Chanana | Expedite | Done | Done | 2021-08-12 | 2021-09-27 |  |  | 2021-08-16 | 2021-08-16 |  |  | 4
2021-08-13 | 2021-08-13 | 2nd. Iteration | [16 empty] | 0
2021-08-14 |  |  | Subtask | Enroll individual device for InTune according to the BYOD terms | DBAAS-6465 | Miguel Martinez | Derek Daigrepont | Medium | Done | Done | 2021-08-14 | 2021-10-14 |  | DBAAS-6440 | 2021-10-14 | 2021-10-14 |  |  | 61
2021-08-14 |  |  | Subtask | Install Slack Client | DBAAS-6460 | Miguel Martinez | Derek Daigrepont | Medium | Done | Done | 2021-08-14 | 2021-09-02 |  | DBAAS-6440 | 2021-09-02 | 2021-09-02 |  |  | 19
2021-08-14 |  |  | Subtask | Update GAL and Profile Information | DBAAS-6459 | Miguel Martinez | Derek Daigrepont | Medium | Done | Done | 2021-08-14 | 2021-08-20 |  | DBAAS-6440 | 2021-08-20 | 2021-08-20 |  |  | 6
2021-08-14 |  |  | Subtask | Install the Zscaler tool | DBAAS-6446 | Miguel Martinez | Derek Daigrepont | Medium | Done | Done | 2021-08-14 | 2021-08-16 |  | DBAAS-6440 | 2021-08-16 | 2021-08-16 |  |  | 2
2021-08-14 |  |  | Subtask | Install tools on developer workstation | DBAAS-6445 | Miguel Martinez | Derek Daigrepont | Medium | Done | Done | 2021-08-14 | 2021-09-03 |  | DBAAS-6440 | 2021-09-03 | 2021-09-03 |  |  | 20
2021-08-14 |  |  | Subtask | Request cloud platform server admin account | DBAAS-6444 | Miguel Martinez | Derek Daigrepont | Medium | Done | Done | 2021-08-14 | 2021-10-20 |  | DBAAS-6440 | 2021-10-20 | 2021-10-20 |  |  | 67
2021-08-14 |  |  | Subtask | Review and understand important DBaaS documentation (policies procedures user guides etc.) | DBAAS-6443 | Miguel Martinez | Derek Daigrepont | Medium | Done | Done | 2021-08-14 | 2021-10-14 |  | DBAAS-6440 | 2021-10-14 | 2021-10-14 |  |  | 61
2021-08-17 |  |  | Subtask | Validate and correct DBaaS Support Cost Report | DBAAS-6477 | Ricardo Martinez | Ricardo Martinez | Medium | Done | Done | 2021-08-17 | 2021-08-20 |  | DBAAS-6470 | 2021-08-20 | 2021-08-20 |  |  | 3
2021-08-17 |  |  | Subtask | Validate and correct Database Assets Reports | DBAAS-6476 | Ricardo Martinez | Ricardo Martinez | Medium | Done | Done | 2021-08-17 | 2021-08-20 |  | DBAAS-6470 | 2021-08-20 | 2021-08-20 |  |  | 3
2021-08-17 |  |  | Subtask | Check an correct DBaaS Scheduled Run Time Dashboard | DBAAS-6472 | Ricardo Martinez | Ricardo Martinez | Medium | Done | Done | 2021-08-17 | 2021-08-19 |  | DBAAS-6469 | 2021-08-17 | 2021-08-17 |  |  | 0
2021-08-17 |  |  | Enhancement | Update PowerBI Reports to correct the number of Instances shown on the Reports | DBAAS-6470 | Ricardo Martinez | Pooja Chanana | High | Done | Done | 2021-08-17 | 2021-10-07 |  |  | 2021-08-26 | 2021-08-26 |  |  | 9
2021-08-17 |  |  | Enhancement | Update Power BI Reports to eliminate any hard coded values | DBAAS-6469 | Ricardo Martinez | Pooja Chanana | Medium | Blocked |  | 2021-08-17 | 2021-10-22 |  |  |  | 2021-10-22 |  |  | 0
2021-08-17 |  |  | Subtask | Validate and correct Database Risk Report | DBAAS-6479 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-08-17 | 2021-08-20 |  | DBAAS-6470 | 2021-08-20 | 2021-08-20 |  |  | 3
2021-08-17 |  |  | Subtask | Validate and correct Support Cost Forecast | DBAAS-6478 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-08-17 | 2021-08-20 |  | DBAAS-6470 | 2021-08-20 | 2021-08-20 |  |  | 3
2021-08-17 |  |  | Subtask | Check and correct Managed DBaaS Support Cost Report | DBAAS-6475 | Eduardo Silva | Ricardo Martinez | Medium | Blocked |  | 2021-08-17 | 2021-11-03 |  | DBAAS-6469 |  | 2021-08-19 |  |  | 0
2021-08-17 |  |  | Subtask | Check and correct Managed DBaaS Supplier Management Report | DBAAS-6474 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-08-17 | 2021-08-25 |  | DBAAS-6469 | 2021-08-25 | 2021-08-25 |  |  | 8
2021-08-17 |  |  | Subtask | Check and correct Managed DBaaS Financial Recovery Analyzer | DBAAS-6473 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-08-17 | 2021-08-20 |  | DBAAS-6469 | 2021-08-20 | 2021-08-20 |  |  | 3
2021-08-20 |  |  | Subtask | Correct right hand table (Determines Unit Pricing / Cost Per Database Instance By Month/Year) in Managed DBaaS Product Rate Card | DBAAS-6488 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-08-20 | 2021-08-24 |  | DBAAS-6470 | 2021-08-24 | 2021-08-24 |  |  | 4
2021-08-20 |  |  | Subtask | Correct Annual Budget Unit Rate by Service grid in Managed DBaaS Product Rate Card | DBAAS-6487 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-08-20 | 2021-08-26 |  | DBAAS-6470 | 2021-08-26 | 2021-08-26 |  |  | 6
2021-08-20 |  |  | Subtask | Correct visuals in Managed DBaaS Support Cost Forecast | DBAAS-6489 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-08-20 | 2021-08-23 |  | DBAAS-6470 | 2021-08-23 | 2021-08-23 |  |  | 3
2021-08-26 |  |  | Enabler Story | Review status & Passwords of attestation of all database instances |  | Leadership Report. PBI | DBAAS-6525 | Eduardo Silva | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-09-29 |  | DBAAS-5814 | 2021-09-29 | 2021-09-29 |  |  | 34
2021-08-26 |  |  | Enabler Story | Review status attestation of all database instancesv View a historical report of all actions by service. Power BI | DBAAS-6523 | Eduardo Silva | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-10-21 |  | DBAAS-5814 | 2021-10-21 | 2021-10-21 |  |  | 56
2021-08-26 |  |  | Enabler Story | Review status of attestation of all database instances | View a report of all actions by service. Power BI | DBAAS-6521 | Eduardo Silva | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-10-21 |  | DBAAS-5814 | 2021-10-21 | 2021-10-21 |  |  | 56
2021-08-26 |  |  | Enabler Story | Notification. Escalation email |  | Send escalation email notification to Portfolio Owner 7 days prior to 90 days after the last attestation. | DBAAS-6519 | Eduardo Silva | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-09-27 |  | DBAAS-5814 | 2021-09-27 | 2021-09-27 |  |  | 32
2021-08-26 |  |  | Enabler Story | Notification. email 14 days prior to 90 days | Send email notification to IT Service Owner 14 days prior to 90 days after the last attestation. (PAutomate) | DBAAS-6516 | Eduardo Silva | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-09-27 |  | DBAAS-5814 | 2021-09-27 | 2021-09-27 |  |  | 32
2021-08-26 |  |  | Enabler Story | Review status of attestation of all database instances List all database instances. (PBI) | DBAAS-6515 | Eduardo Silva | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-09-29 |  | DBAAS-5814 | 2021-09-29 | 2021-09-29 | DBAAS-6514 |  | 34
2021-08-26 |  |  | Enabler Story | SECOND PHASE ServiceNow. Service request Create ServiceNow service request assigned to IT Service Owner 14 days prior to 90 days after the last attestation. (TBC) | DBAAS-6518 | Fabian Ponce | Fabian Ponce | Medium | Blocked |  | 2021-08-26 | 2021-10-22 |  | DBAAS-5814 |  | 2021-10-22 | DBAAS-6306 |  | 0
2021-08-26 |  |  | Enabler Story | Notification. email 14 days prior to 90 days | DBAAS-6517 | Fabian Ponce | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-09-28 |  | DBAAS-5814 | 2021-09-20 | 2021-09-20 |  |  | 25
2021-08-26 |  |  | Enabler Story | Attest List all database instances with more than 76 days since last attestation with options to attest. PAPPS | DBAAS-6513 | Fabian Ponce | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-09-28 |  | DBAAS-5814 | 2021-09-20 | 2021-09-20 | DBAAS-6514;DBAAS-6537 |  | 25
2021-08-26 |  |  | Enabler Story | PAPPS. Make changes to Default Screen | DBAAS-6522 | Ricardo Martinez | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-09-21 |  | DBAAS-5814 | 2021-09-21 | 2021-09-21 |  |  | 26
2021-08-26 |  |  | Enabler Story | Attest List all database instances with editable attestation data. PAPPS | DBAAS-6514 | Ricardo Martinez | Fabian Ponce | Medium | Done | Done | 2021-08-26 | 2021-09-29 |  | DBAAS-5814 | 2021-09-20 | 2021-09-20 | DBAAS-6515;DBAAS-6513 |  | 25
2021-08-30 |  |  | Subtask | PAPPS. Use RLS to display the data for the logged user. History for edition. Where Dt_Diff_Att < 20 Days (TBD) | DBAAS-6538 | Ricardo Martinez | Fabian Ponce | Medium | Done | Done | 2021-08-30 | 2021-09-20 |  | DBAAS-6514 | 2021-09-20 | 2021-09-20 | DBAAS-6537 |  | 21
2021-08-30 |  |  | Subtask | SQL. SP/VIEW. To display data to PBI/PAPPS by [IT Service Owner] OR [Portfolio Owner] AND Dt_Diff_Att < 20 ΓÇª Not for DBaaS Team Member | DBAAS-6537 | Miguel Martinez | Fabian Ponce | Medium | Done | Done | 2021-08-30 | 2021-09-20 |  | DBAAS-6514 | 2021-09-20 | 2021-09-20 | DBAAS-6538;DBAAS-6513 |  | 21
2021-08-30 |  |  | Subtask | PAPPS. Use RLS to display the data for the logged user. | DBAAS-6536 | Miguel Martinez | Fabian Ponce | Medium | Done | Done | 2021-08-30 | 2021-09-20 |  | DBAAS-6513 | 2021-09-20 | 2021-09-20 | DBAAS-6535 |  | 21
2021-08-30 |  |  | Subtask | SQL. SP/VIEW. To display data to PBI/PAPPS by [IT Service Owner] OR [Portfolio Owner] AND Dt_Diff_Att >=76 ΓÇª Not for DBaaS Team Member | DBAAS-6535 | Fabian Ponce | Fabian Ponce | Medium | Done | Done | 2021-08-30 | 2021-09-10 |  | DBAAS-6513 | 2021-09-10 | 2021-09-10 | DBAAS-6536;DBAAS-6534 |  | 11
2021-08-30 |  |  | Subtask | SQL. Create table DBASS_ACCOUNT_ATTESTATION_LOG for tracking status | DBAAS-6534 | Fabian Ponce | Fabian Ponce | Medium | Done | Done | 2021-08-30 | 2021-09-17 |  | DBAAS-6513 | 2021-09-17 | 2021-09-17 | DBAAS-6535;DBAAS-6533 |  | 18
2021-08-30 |  |  | Subtask | SQL. Extract data from SP to populate work tables. | DBAAS-6533 | Fabian Ponce | Fabian Ponce | Medium | Done | Done | 2021-08-30 | 2021-09-13 |  | DBAAS-6513 | 2021-09-13 | 2021-09-13 | DBAAS-6534 |  | 14
2021-09-03 |  |  | Enhancement | Update Product Rate Card Power BI report | DBAAS-6689 | Eduardo Silva | Pooja Chanana | Medium | Done | Done | 2021-09-03 | 2021-10-19 |  |  | 2021-09-17 | 2021-09-17 |  |  | 14
2021-09-14 |  |  | Enhancement | Define CI/CD Pipeline Procedure for Stored Procedure Changes | DBAAS-6733 | Fabian Ponce | Pooja Chanana | Medium | Ready for Analysis |  | 2021-09-14 | 2021-10-22 |  | DBAAS-6735 |  | 2021-09-14 |  |  | 0
2021-09-14 |  |  | Enabler Story | Conceptualize Design for DBAAS6735 | DBAAS-6736 | Julio Alcala | Automation for Jira | Medium | Done | Done | 2021-09-14 | 2021-10-21 |  | DBAAS-6735 | 2021-10-21 | 2021-10-21 |  |  | 37
2021-09-14 |  |  | Feature | Implement Procedures Incorporating PowerBI Pipeline in the CI/CD Process | DBAAS-6735 | Julio Alcala | Pooja Chanana | Medium | In Design |  | 2021-09-14 | 2021-10-20 | 2021-12-17 |  |  | 2021-10-06 |  |  | 0
2021-09-14 |  |  | Enhancement | Define and Document CI/CD Pipeline Procedure for Power BI Dataset Changes | DBAAS-6734 | Julio Alcala | Pooja Chanana | Medium | Ready for Analysis |  | 2021-09-14 | 2021-10-22 |  | DBAAS-6735 |  | 2021-09-14 |  |  | 0
2021-09-17 | 2021-09-17 | Phase 1 | [16 empty] | 0
2021-09-20 |  |  | Enabler Story | Conceptualize Design for DBAAS6943 | DBAAS-6944 | Julio Alcala | Automation for Jira | Medium | Done | Done | 2021-09-20 | 2021-10-22 |  | DBAAS-6943 | 2021-10-22 | 2021-10-22 |  |  | 32
2021-09-20 |  |  | Enabler Story | PAPPS. Add error control for the bulk attestation flow | DBAAS-6964 | Miguel Martinez | Ricardo Martinez | Medium | Done | Done | 2021-09-20 | 2021-10-22 |  | DBAAS-5814 | 2021-10-22 | 2021-10-22 |  |  | 32
2021-09-20 |  |  | Enabler Story | PAPPS. Send Logs to logs table. | DBAAS-6962 | Miguel Martinez | Ricardo Martinez | Medium | Done | Done | 2021-09-20 | 2021-09-23 |  | DBAAS-5814 | 2021-09-23 | 2021-09-23 |  |  | 3
2021-09-20 |  |  | Enabler Story | PAPPS. Change Review Screen to work only as comments instead of Chat | DBAAS-6950 | Miguel Martinez | Ricardo Martinez | Medium | Done | Done | 2021-09-20 | 2021-09-22 |  | DBAAS-5814 | 2021-09-22 | 2021-09-22 |  |  | 2
2021-09-20 |  |  | Feature | PowerBI Report for Recoverability Status for all DBaaS Hosted Database Instances | DBAAS-6943 | Miguel Martinez | Pooja Chanana | Medium | Ready for Design |  | 2021-09-20 | 2021-10-22 | 2021-12-17 |  |  | 2021-09-20 | DBAAS-4462 |  | 0
2021-09-20 |  |  | Enabler Story | PAPPS. Builtin manual user or maybe in PBI | DBAAS-6963 | Ricardo Martinez | Ricardo Martinez | Medium | Ready for Analysis |  | 2021-09-20 | 2021-10-12 |  | DBAAS-5814 |  | 2021-09-20 |  |  | 0
2021-09-20 |  |  | Enabler Story | SECOND PHASE PAPPS. Create FAQs screen | DBAAS-6961 | Ricardo Martinez | Ricardo Martinez | Medium | Ready for Analysis |  | 2021-09-20 | 2021-10-22 |  | DBAAS-5814 |  | 2021-09-20 |  |  | 0
2021-09-20 |  |  | Enabler Story | PBI. Change columns sent to the PAPPS and correct look and feel | DBAAS-6960 | Ricardo Martinez | Ricardo Martinez | Medium | Done | Done | 2021-09-20 | 2021-09-22 |  | DBAAS-5814 | 2021-09-22 | 2021-09-22 |  |  | 2
2021-09-20 |  |  | Enabler Story | PAPPS. Use RLS to display the data for the logged user. | DBAAS-6947 | Ricardo Martinez | Miguel Martinez | Medium | Blocked |  | 2021-09-20 | 2021-11-01 |  | DBAAS-5814 |  | 2021-09-20 | DBAAS-7131 |  | 0
2021-09-20 |  |  | Enabler Story | SQL. Change Attestation table and Massive Update SP for comments instead of review | DBAAS-6951 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-09-20 | 2021-09-28 |  | DBAAS-5814 | 2021-09-22 | 2021-09-22 |  |  | 2
2021-09-20 |  |  | Enabler Story | SQL. Change messages table to work for Comments instead of Chat | DBAAS-6949 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-09-20 | 2021-09-28 |  | DBAAS-5814 | 2021-09-23 | 2021-09-23 |  |  | 3
2021-09-22 |  |  | Build Story | Modify the DBaaS Database Instance PowerBI report to include the Last_Login_Date for Database Instances | DBAAS-7008 | Ricardo Martinez | Pooja Chanana | Medium | Done | Done | 2021-09-22 | 2021-09-29 |  | DBAAS-7003 | 2021-09-24 | 2021-09-24 | DBAAS-7007 |  | 2
2021-09-23 |  |  | Enabler Story | SQL. SP to send log of email notifications | DBAAS-7017 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-09-23 | 2021-10-27 |  | DBAAS-5814 | 2021-10-27 | 2021-10-27 | DBAAS-7330 |  | 34
2021-09-23 |  |  | Enabler Story | PAUTOMATE. Adapt email notification flow to run log SP | DBAAS-7018 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-09-23 | 2021-09-29 |  | DBAAS-5814 | 2021-09-29 | 2021-09-29 |  |  | 6
2021-09-27 |  |  | Enabler Story | Power Automate should add the logs to the notifications email | DBAAS-7036 | Eduardo Silva | Eduardo Silva | Medium | Done | Done | 2021-09-27 | 2021-10-05 |  | DBAAS-5814 | 2021-10-05 | 2021-10-05 |  |  | 8
2021-09-27 |  |  | Enabler Story | SQL. Adapt SP that feeds PAUTOMATE | DBAAS-7037 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-09-27 | 2021-09-29 |  | DBAAS-5814 | 2021-09-29 | 2021-09-29 |  |  | 2
2021-09-27 |  |  | Enabler Story | PBI. Test direct query connection with custom SQL query | DBAAS-7045 | Ricardo Martinez | Miguel Martinez | Medium | Done | Done | 2021-09-27 | 2021-10-14 |  | DBAAS-5814 | 2021-10-12 | 2021-10-12 |  |  | 15
2021-09-27 |  |  | Enhancement | Enhance the AWS Storage Report PowerBI Report To Include IaaS DBaaS Provisioned Instances | DBAAS-7041 | Julio Alcala | Pooja Chanana | Medium | Ready for Analysis |  | 2021-09-27 | 2021-10-19 |  |  |  | 2021-10-19 | DBAAS-7019 |  | 0
2021-09-28 |  |  | Enabler Story | SQL. Modify eMail SP Notification | DBAAS-7048 | Fabian Ponce | Fabian Ponce | Medium | Done | Done | 2021-09-28 | 2021-10-12 |  | DBAAS-5814 | 2021-09-28 | 2021-09-28 |  |  | 0
2021-10-01 | 2021-10-01 | Phase 2 | [16 empty] | 0
2021-10-05 |  |  | Enabler Story | Notify the database instance owner and Portfolio Owner based on the quarters of the year | DBAAS-7094 | Eduardo Silva | Eduardo Silva | Medium | Done | Done | 2021-10-05 | 2021-10-21 |  | DBAAS-5814 | 2021-10-21 | 2021-10-21 |  |  | 16
2021-10-06 |  |  | Enabler Story | Reenable Attestion App DEV environment | DBAAS-7105 | Eduardo Silva | Miguel Martinez | Medium | Done | Done | 2021-10-06 | 2021-10-06 |  | DBAAS-5814 | 2021-10-06 | 2021-10-06 |  |  | 0
2021-10-06 |  |  | Enabler Story | Test the Attestation App with multiple concurrent users | DBAAS-7106 | Ricardo Martinez | Miguel Martinez | Medium | Done | Done | 2021-10-06 | 2021-10-06 |  | DBAAS-5814 | 2021-10-06 | 2021-10-06 |  |  | 0
2021-10-08 |  |  | Enabler Story | Test the Attestation Solution in the different Browser | DBAAS-7111 | Eduardo Silva | Julio Alcala | Medium | Done | Done | 2021-10-08 | 2021-10-25 | 2021-10-22 | DBAAS-5814 | 2021-10-25 | 2021-10-25 |  |  | 17
2021-10-12 |  |  | Enabler Story | SQL. Redesign database structure | DBAAS-7120 | Fabian Ponce | Fabian Ponce | Medium | Done | Done | 2021-10-12 | 2021-10-14 |  | DBAAS-5814 | 2021-10-14 | 2021-10-14 |  |  | 2
2021-10-12 |  |  | Enabler Story | PBI. Make the App usable for users without connection permissions | DBAAS-7131 | Ricardo Martinez | Ricardo Martinez | Medium | Ready for Design |  | 2021-10-12 | 2021-11-01 | 2021-11-12 | DBAAS-5814 |  | 2021-10-12 | DBAAS-6947 |  | 0
2021-10-12 |  |  | Enabler Story | PBI. Test direct query connection with joined tables. | DBAAS-7126 | Miguel Martinez | Miguel Martinez | Medium | Done | Done | 2021-10-12 | 2021-10-12 |  | DBAAS-5814 | 2021-10-12 | 2021-10-12 |  |  | 0
2021-10-12 |  |  | Enabler Story | Set up Attestation App with new database structure | DBAAS-7125 | Miguel Martinez | Miguel Martinez | Medium | Done | Done | 2021-10-12 | 2021-10-19 |  | DBAAS-5814 | 2021-10-19 | 2021-10-19 |  |  | 7
2021-10-14 |  |  | Enhancement | Remove Portfolio Owner related columns from Power BI reports | DBAAS-7169 | Miguel Martinez | Miguel Martinez | Medium | Done | Done | 2021-10-14 | 2021-10-27 | 2021-10-29 |  | 2021-10-27 | 2021-10-27 |  |  | 13
2021-10-14 |  |  | Enhancement | Enhance DBaaS Database Assets Power BI report to display the Cloud Provider version | DBAAS-7172 | Fabian Ponce | Pooja Chanana | Medium | In Design |  | 2021-10-14 | 2021-11-02 | 2021-11-12 |  |  | 2021-10-29 | DBAAS-7124 |  | 0
2021-10-19 |  |  | Enabler Story | SQL. Modify batch update SP to send the required columns to the Log Table | DBAAS-7203 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-10-19 | 2021-10-22 |  | DBAAS-5814 | 2021-10-22 | 2021-10-22 | DBAAS-7204;DBAAS-7202 |  | 3
2021-10-19 |  |  | Enabler Story | SQL. Create Log Table with the required columns | DBAAS-7202 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-10-19 | 2021-10-21 |  | DBAAS-5814 | 2021-10-21 | 2021-10-21 | DBAAS-7203 |  | 2
2021-10-19 |  |  | Enabler Story | SQL. Create daily SP that refreshes the data to the Attestation Table | DBAAS-7201 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-10-19 | 2021-10-21 |  | DBAAS-5814 | 2021-10-21 | 2021-10-21 |  |  | 2
2021-10-19 |  |  | Enabler Story | PBI. Modify the log report with the new table structure | DBAAS-7207 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-10-19 | 2021-11-02 |  | DBAAS-5814 | 2021-10-28 | 2021-10-28 | DBAAS-7205 |  | 9
2021-10-19 |  |  | Enabler Story | PAUTOMATE. Modify the flow that triggers the SP so that it retrieves the required columns from the app | DBAAS-7204 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-10-19 | 2021-10-25 |  | DBAAS-5814 | 2021-10-25 | 2021-10-25 | DBAAS-7205;DBAAS-7203 |  | 6
2021-10-19 |  |  | Task | Enable refresh of DBaaS Database Collection Connectivity Report on DBaaS Platform workspace | DBAAS-7195 | Eduardo Silva | Susie Llinas | Medium | Done | Done | 2021-10-19 | 2021-10-19 |  |  | 2021-10-19 | 2021-10-19 |  |  | 0
2021-10-19 |  |  | Enabler Story | PAPPS. Modify the flow run so that it sends the required columns | DBAAS-7205 | Miguel Martinez | Ricardo Martinez | Medium | Done | Done | 2021-10-19 | 2021-10-25 |  | DBAAS-5814 | 2021-10-25 | 2021-10-25 | DBAAS-7207;DBAAS-7204 |  | 6
2021-10-19 |  |  | Enabler Story | Test the pipeline process from Local Environment Dev UAT PROD | DBAAS-7198 | Miguel Martinez | Julio Alcala | Medium | Ready for Analysis |  | 2021-10-19 | 2021-10-22 |  | DBAAS-6735 |  | 2021-10-19 |  |  | 0
2021-10-19 |  |  | Enabler Story | Evaluate the need of UAT Environment | DBAAS-7199 | Julio Alcala | Julio Alcala | Medium | Ready for Analysis |  | 2021-10-19 | 2021-10-20 |  | DBAAS-6735 |  | 2021-10-19 |  |  | 0
2021-10-19 |  |  | Enabler Story | Setup the security for each workspace | DBAAS-7197 | Julio Alcala | Julio Alcala | Medium | Ready for Analysis |  | 2021-10-19 | 2021-10-22 |  | DBAAS-6735 |  | 2021-10-19 |  |  | 0
2021-10-19 |  |  | Build Story | Setup the DEV & UAT Workspace from DBaaS Workspace in the Pipeline | DBAAS-7196 | Julio Alcala | Julio Alcala | Medium | in Build |  | 2021-10-19 | 2021-11-03 | 2021-11-05 | DBAAS-6735 |  | 2021-10-21 |  |  | 0
2021-10-19 |  |  | Enabler Story | Modifications for stakeholders demo | DBAAS-7206 | Ricardo Martinez | Ricardo Martinez | Medium | Done | Done | 2021-10-19 | 2021-10-19 |  | DBAAS-5814 | 2021-10-19 | 2021-10-19 |  |  | 0
2021-10-19 |  |  | Enabler Story | Create the Power BI APP that will be used for DBaaS Workspace | DBAAS-7200 | Ricardo Martinez | Julio Alcala | Medium | Ready for Analysis |  | 2021-10-19 | 2021-10-22 |  | DBAAS-6735 |  | 2021-10-19 |  |  | 0
2021-10-20 |  |  | Enabler Story | PBI & PAPPS. Make proposed modifications in meeting with stakeholders | DBAAS-7285 | Ricardo Martinez | Ricardo Martinez | Medium | Blocked |  | 2021-10-20 | 2021-10-29 | 2021-11-05 | DBAAS-5814 |  | 2021-10-20 |  |  | 0
2021-10-21 |  |  | Enabler Story | PAPPS. Create connection to CATALOGS table | DBAAS-7305 | Ricardo Martinez | Ricardo Martinez | Medium | Done | Done | 2021-10-21 | 2021-10-22 |  | DBAAS-5814 | 2021-10-22 | 2021-10-22 |  |  | 1
2021-10-21 |  |  | Enabler Story | SQL. Create CATALOGS table to handle Rationale and future catalogs | DBAAS-7304 | Ricardo Martinez | Ricardo Martinez | Medium | Done | Done | 2021-10-21 | 2021-10-21 |  | DBAAS-5814 | 2021-10-21 | 2021-10-21 |  |  | 0
2021-10-22 |  |  | Enabler Story | PAPPS. Create Flag capability to each row | DBAAS-7320 | Ricardo Martinez | Ricardo Martinez | Medium | Done | Done | 2021-10-22 | 2021-10-26 |  | DBAAS-5814 | 2021-10-26 | 2021-10-26 |  |  | 4
2021-10-22 |  |  | Enabler Story | Confirm how to apply the Rationale to each DBI | DBAAS-7316 | Ricardo Martinez | Ricardo Martinez | Medium | Done | Done | 2021-10-22 | 2021-10-26 |  | DBAAS-5814 | 2021-10-22 | 2021-10-22 | DBAAS-7319 |  | 0
2021-10-22 |  |  | Build Story | Implementation of CI/CD Pipeline for Attestation App | DBAAS-7315 | Miguel Martinez | Julio Alcala | Medium | Ready for Analysis |  | 2021-10-22 | 2021-10-22 | 2021-11-05 | DBAAS-5814 |  | 2021-10-22 |  |  | 0
2021-10-22 |  |  | Feature | Create documentation for the report Optimization of Oracle Database License Cost | DBAAS-7317 | Eduardo Silva | Eduardo Silva | Medium | Done | Done | 2021-10-22 | 2021-10-25 |  |  | 2021-10-25 | 2021-10-25 |  |  | 3
2021-10-22 |  |  | Enabler Story | SQL. Create a SP to insert/update the new combobox Rationale option in the Attestation web app | DBAAS-7319 | Fabian Ponce | Fabian Ponce | Medium | Done | Done | 2021-10-22 | 2021-10-27 |  | DBAAS-5814 | 2021-10-27 | 2021-10-27 | DBAAS-7316 |  | 5
2021-10-25 |  |  | Enabler Story | SQL. Modify the SP that send data to PAutomate for email notifications. | DBAAS-7331 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-10-25 | 2021-10-28 |  | DBAAS-5814 | 2021-10-28 | 2021-10-28 | DBAAS-7330 |  | 3
2021-10-25 |  |  | Enabler Story | Conceptualize Design for DBAAS7334 | DBAAS-7335 | Julio Alcala | Automation for Jira | Medium | Ready for Design |  | 2021-10-25 | 2021-10-26 |  | DBAAS-7334 |  | 2021-10-25 |  |  | 0
2021-10-25 |  |  | Feature | Build Collection and Develop Power BI Report to display Pending Maintenance on AWS RDS Database Instances | DBAAS-7334 | Julio Alcala | Pooja Chanana | Medium | Ready for Analysis |  | 2021-10-25 | 2021-10-25 |  |  |  | 2021-10-25 | DBAAS-7214 |  | 0
2021-10-25 |  |  | Enabler Story | PAUTOMATE. Modify flow to send email notifications. | DBAAS-7330 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-10-25 | 2021-11-02 |  | DBAAS-5814 | 2021-10-28 | 2021-10-28 | DBAAS-7017;DBAAS-7331 |  | 3
2021-10-25 |  |  | Enabler Story | Documentation for the new report Optimization of Oracle Database License Cost | DBAAS-7326 | Eduardo Silva | Eduardo Silva | Medium | Blocked |  | 2021-10-25 | 2021-11-03 |  |  |  | 2021-10-25 |  |  | 0
2021-10-25 |  |  | Build Story | Create Documentation around the report | DBAAS-7333 | Miguel Martinez | Julio Alcala | Medium | Ready for Analysis |  | 2021-10-25 | 2021-10-25 |  | DBAAS-6943 |  | 2021-10-25 |  |  | 0
2021-10-28 |  |  | Enabler Story | Set up the Attestation app in Power Apps with the new DB SYNATT schema | DBAAS-7376 | Miguel Martinez | Miguel Martinez | Medium | Done | Done | 2021-10-28 | 2021-11-02 | 2021-11-05 | DBAAS-5814 | 2021-11-02 | 2021-11-02 | DBAAS-7378;DBAAS-7379 |  | 5
2021-10-28 |  |  | Enabler Story | Set up the Attestation app and reports in Power BI with the new DB SYNATT schema | DBAAS-7377 | Ricardo Martinez | Miguel Martinez | Medium | Done | Done | 2021-10-28 | 2021-11-02 |  | DBAAS-5814 | 2021-11-02 | 2021-11-02 | DBAAS-7379 |  | 5
2021-10-28 |  |  | Enabler Story | Set up the Attestation app flows in Power Automate with the new DB SYNATT schema | DBAAS-7378 | Eduardo Silva | Miguel Martinez | Medium | Done | Done | 2021-10-28 | 2021-11-02 | 2021-11-05 | DBAAS-5814 | 2021-11-01 | 2021-11-01 | DBAAS-7376;DBAAS-7379 |  | 4
2021-10-28 |  |  | Enabler Story | Recreate the Attestation app database objects in the new databse SYNATT schema | DBAAS-7379 | Fabian Ponce | Miguel Martinez | Medium | Done | Done | 2021-10-28 | 2021-11-02 | 2021-11-05 | DBAAS-5814 | 2021-11-02 | 2021-11-02 | DBAAS-7376;DBAAS-7377;DBAAS-7378 |  | 5

## Done Last Week
DT | DT_SPRINT | SPRINT | Issue_Type | Summary | Key | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due_date | parent | Resolved | Status_Category_Changed | Linked_Issues | Parent_Link | Time Resolution
2021-10-28 |  |  | Enabler Story | Set up the Attestation app flows in Power Automate with the new DB SYNATT schema | DBAAS-7378 | Eduardo Silva | Miguel Martinez | Medium | Done | Done | 2021-10-28 | 2021-11-02 | 2021-11-05 | DBAAS-5814 | 2021-11-01 | 2021-11-01 | DBAAS-7376;DBAAS-7379 |  | 4
2021-10-25 |  |  | Enabler Story | PAUTOMATE. Modify flow to send email notifications. | DBAAS-7330 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-10-25 | 2021-11-02 |  | DBAAS-5814 | 2021-10-28 | 2021-10-28 | DBAAS-7017;DBAAS-7331 |  | 3
2021-10-19 |  |  | Enabler Story | PBI. Modify the log report with the new table structure | DBAAS-7207 | Eduardo Silva | Ricardo Martinez | Medium | Done | Done | 2021-10-19 | 2021-11-02 |  | DBAAS-5814 | 2021-10-28 | 2021-10-28 | DBAAS-7205 |  | 9
2021-10-28 |  |  | Enabler Story | Recreate the Attestation app database objects in the new databse SYNATT schema | DBAAS-7379 | Fabian Ponce | Miguel Martinez | Medium | Done | Done | 2021-10-28 | 2021-11-02 | 2021-11-05 | DBAAS-5814 | 2021-11-02 | 2021-11-02 | DBAAS-7376;DBAAS-7377;DBAAS-7378 |  | 5
2021-10-25 |  |  | Enabler Story | SQL. Modify the SP that send data to PAutomate for email notifications. | DBAAS-7331 | Fabian Ponce | Ricardo Martinez | Medium | Done | Done | 2021-10-25 | 2021-10-28 |  | DBAAS-5814 | 2021-10-28 | 2021-10-28 | DBAAS-7330 |  | 3
2021-10-28 |  |  | Enabler Story | Set up the Attestation app in Power Apps with the new DB SYNATT schema | DBAAS-7376 | Miguel Martinez | Miguel Martinez | Medium | Done | Done | 2021-10-28 | 2021-11-02 | 2021-11-05 | DBAAS-5814 | 2021-11-02 | 2021-11-02 | DBAAS-7378;DBAAS-7379 |  | 5
2021-10-28 |  |  | Enabler Story | Set up the Attestation app and reports in Power BI with the new DB SYNATT schema | DBAAS-7377 | Ricardo Martinez | Miguel Martinez | Medium | Done | Done | 2021-10-28 | 2021-11-02 |  | DBAAS-5814 | 2021-11-02 | 2021-11-02 | DBAAS-7379 |  | 5

## Blocked
DT | DT_SPRINT | SPRINT | Issue_Type | Summary | Key | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due_date | parent | Resolved | Status_Category_Changed | Linked_Issues | Parent_Link | Time Resolution
2021-02-26 |  |  | Build Story | Develop Report for the Optimization of Oracle Database License Cost | DBAAS-4923 | Eduardo Silva | Erik Solis | High | Blocked |  | 2021-02-26 | 2021-11-03 | 2021-11-05 | DBAAS-4507 |  | 2021-09-23 |  |  | 0
2021-07-16 |  |  | Enhancement | Enhance the DBaaS Database Assets Report with Auto Minor Version Update Column | DBAAS-6164 | Eduardo Silva | Pooja Chanana | Medium | Blocked |  | 2021-07-16 | 2021-10-22 | 2021-09-17 |  |  | 2021-07-16 | DBAAS-2263;DBAAS-5835 |  | 0
2021-07-28 |  |  | Enabler Story | Research the capability to create a ticket in ServiceNow from the chosen web tool | DBAAS-6306 | Fabian Ponce | Pooja Chanana | Medium | Blocked |  | 2021-07-28 | 2021-10-22 |  | DBAAS-5814 |  | 2021-10-22 | DBAAS-6518 |  | 0
2021-08-17 |  |  | Subtask | Check and correct Managed DBaaS Support Cost Report | DBAAS-6475 | Eduardo Silva | Ricardo Martinez | Medium | Blocked |  | 2021-08-17 | 2021-11-03 |  | DBAAS-6469 |  | 2021-08-19 |  |  | 0
2021-08-17 |  |  | Enhancement | Update Power BI Reports to eliminate any hard coded values | DBAAS-6469 | Ricardo Martinez | Pooja Chanana | Medium | Blocked |  | 2021-08-17 | 2021-10-22 |  |  |  | 2021-10-22 |  |  | 0
2021-08-26 |  |  | Enabler Story | SECOND PHASE ServiceNow. Service request Create ServiceNow service request assigned to IT Service Owner 14 days prior to 90 days after the last attestation. (TBC) | DBAAS-6518 | Fabian Ponce | Fabian Ponce | Medium | Blocked |  | 2021-08-26 | 2021-10-22 |  | DBAAS-5814 |  | 2021-10-22 | DBAAS-6306 |  | 0
2021-09-20 |  |  | Enabler Story | PAPPS. Use RLS to display the data for the logged user. | DBAAS-6947 | Ricardo Martinez | Miguel Martinez | Medium | Blocked |  | 2021-09-20 | 2021-11-01 |  | DBAAS-5814 |  | 2021-09-20 | DBAAS-7131 |  | 0
2021-10-20 |  |  | Enabler Story | PBI & PAPPS. Make proposed modifications in meeting with stakeholders | DBAAS-7285 | Ricardo Martinez | Ricardo Martinez | Medium | Blocked |  | 2021-10-20 | 2021-10-29 | 2021-11-05 | DBAAS-5814 |  | 2021-10-20 |  |  | 0
2021-10-25 |  |  | Enabler Story | Documentation for the new report Optimization of Oracle Database License Cost | DBAAS-7326 | Eduardo Silva | Eduardo Silva | Medium | Blocked |  | 2021-10-25 | 2021-11-03 |  |  |  | 2021-10-25 |  |  | 0

## Lifecycle Activity for Database
Lifecycle Activity for Database Instance Account Compliance Collection - Database and Containers - Confluence (atlassian.net)
Lifecycle Activity for Database Instance Account Compliance Collection